## Sheet1
ID | Date raised | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions | Status | Useful resources
1 | 2022-05-13 | Engineer onsite timeframe needs to be consecutive days and end before the 28th. | Medium | High | High | Erik Belle | Discuss with customer during kickoff call to evaluate timeframe. Work with staffing agent to find backup engineer. | Erik to work with staffing agent to get project re-scheduled with new engineer. | Closed | Complete
2 | 2022-05-16 | Engineer cannot access part of building. | Low | Low | Low | Lennet Gallow | Lennet to discuss with Bill on how to move forward with survey. Sammy to move on to different part of building until access is granted. | Lennet, Bill, Sammy, and Erik to hold a status call to go over project scope and building access. | Problem arose at end of day 5/23, Lennet will contact Bill first thing in the morning. | Open
3 | 2022-05-19 | Lack of communication from customer with tight turnaround window. | Medium | Medium | Medium | Erik Belle | Interject on email chain to followup and directly call customer to restate the engineers question and to explain the tight timeframe. | Erik to followup with account manager and have them approach customer. | Closed | Complete

## Common Risks Reference
ID | Date raised | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Severity Rating based on impact & likelihood. | Owner Person who will manage the risk. | Mitigating action Actions to mitigate the risk e.g. reduce the likelihood. | Contingent action Action to be taken if the risk happens. | Progress on actions | Status | Useful resources
|  | Project purpose and need is not well-defined. | Medium | High | High | Project Sponsor | Complete a business case if not already provided and ensure purpose is well defined on Project Charter and PID. | Escalate to the Project Board with an assessment of the risk of runaway costs/never-ending project. |  |  | Business Case Template | Common risks with potential mitigating and contingent actions used as examples to pull from.
|  | Project design and deliverable definition is incomplete. | Low | High | High | Project Sponsor | Define the scope in detail via design workshops with input from subject matter experts. | Document assumptions made and associated risks. Request high risk items that are ill-defined are removed from scope. |  |  | Assumptions Log
|  | Project schedule is not clearly defined or understood | Low | Medium | Medium | Project Manager | Hold scheduling workshops with the project team so they understand the plan and likelihood of missed tasks is reduced. | Share the plan and go through upcoming tasks at each weekly project progress meeting. |  |  | Project Status Template
|  | No control over staff priorities | Medium | Medium | Medium | Project Manager | The Project Sponsor will brief team managers on the importance of the project. Soft book resources as early as possible and then communicate final booking dates asap after the scheduling workshops. Identify back ups for each human resource on the project. | Escalate to the Project Sponsor and bring in back up resource. |  |  | Who is the Project Sponsor?
|  | Consultant or contractor delays | Medium | High | High | Project Manager | Include late penalties in contracts. Build in and protect lead time in the schedule. Communicate schedule early. Check in with suppliers regularly. Query '90% done'. Ask again and again if they need anything else. | Escalate to Project Sponsor and Contracts Manager. Implement late clauses. |  |  | What is lead time?
|  | Estimating and/or scheduling errors | Medium | High | High | Project Manager | Break this risk into two: 'cost estimating' and 'scheduling errors'. Use two methods of cost estimation, and carefully track costs and forecast cost at completion making adjustments as necessary. Build in 10% contingency on cost and scheduling. Track schedules daily and include schedule review as an agenda item in every project team meeting. Flag forecast errors and/or delays to the Project Board early. | Escalate to project sponsor and project board. Raise change request for change to budget or schedule. Pull down contingency. |  |  | Change Request Template
|  | Unplanned work that must be accommodated | Low | High | Medium | Team Manager | Attend project scheduling workshops. Check previous projects, for actual work and costs. Check all plans and quantity surveys. Document all assumptions made in planning and communicate to the project manager before project kick off. | Escalate to the Project Manager with plan of action, including impact on time, cost and quality. |  |  | What is a Project Schedule?
|  | Lack of communication, causing lack of clarity and confusion. | Medium | Medium | Medium | Project Manager | Write a communication plan which includes frequency, goal, and audience of each communication. Identify stakeholders early and make sure they are considered I the communication plan. Use most appropriate channel of communication for audience e.g. don't send 3 paragraph email to Developers, have a call instead. | Correct misunderstandings immediately. Clarify areas that are not clear swiftly using assistance from Project Sponsor if needed. |  |  | Stakeholder Identification
|  | Pressure to arbitrarily reduce task durations and or run tasks in parallel which would increase risk of errors. | Low | High | Medium | Project Manager | Share the schedule with key stakeholders to reduce the risk of this happening. Patiently explain that schedule was built using the expertise of subject matter experts. Explain the risks of the changes. Share the Dennis Lock quote at https://www.stakeholdermap.com/plan-project/plan-reduction-crashing.html. | Escalate to Project Board with assessment of risk and impact of the change. Hold emergency risk management call with decision makers & source of pressure and lay out risk and impact. |  |  | Risks of crashing project plans
|  | Scope creep | Medium | High | High | Project Manager | Document the project scope in a Project Initiation Document or Project Charter and get it authorised by the Project Board. Refer to it throughout the project and assess all changes against it also ensuring alignment of any changes with the Business Case. | Document each and every example of scope creep NO MATTER HOW SMALL in a change order and get authorisation from the project board BEFORE STARTING WORK. This includes ZERO COST changes. |  |  | Project Initiation Document Template
|  | Unresolved project conflicts not escalated in a timely manner | Low | Medium | Medium | Project Manager | Hold regular project team meetings and look out for conflicts. Review the project plan and stakeholder engagement plan for potential areas of conflict. | When aware immediately escalate to Project Board and gain assistance from Project Sponsor to resolve the conflict. |  |  | Stakeholder Management Templates
|  | Business Case becomes obsolete or is undermined by external or internal changes. | Low | High | High | Project Sponsor | No ability to reduce likelihood, but make sure early warning is given by reviewing business case on regular basis with the Project Board. | Initiate escalation and project close down procedure. |  |  | Busines Case Template
|  | Delay in earlier project phases jeopardizes ability to meet fixed date. For example delivery of just in time materials, for conference or launch date. | Medium | High | High | Project Manager | Ensure the project plan is as accurate as possible using scheduling workshops and work breakdown structure. Use Tracking Gantt and Baseline to identify schedule slippage early. | Consider insurance to cover costs and alternative supplier as a back up. |  |  | Work Breakdown Structures
|  | Added workload or time requirements because of new direction, policy, or statute | Low | Medium | Medium | Project Sponsor | No ability to reduce likelihood. | Consider insurance and use Project Board to get advance notice if possible. |  |  | What is the Project Board?
|  | Inadequate customer testing leads to large post go live snag list. | High | High | High | Project Manager | Ensure customer prepares test cases/quality checks and protect testing/quality assurance window. | Raise risk immediately and raise issue if it is clear testing inadequate. Customer could extend testing & bring in additional resource.
|  | Legal action delays or pauses project. | Low | Medium | Medium | Project Sponsor | Ensure all contracts signed before starting the project. Follow all regulatory requirements and complete stakeholder management plan. | Escalate to Project Board who will notify legal department. Follow instructions from legal. |  |  | Stakeholder Management Templates
|  | Customer refuses to approve deliverables/milestones or delays approval, putting pressure on project manager to 'work at risk'. | Medium | Medium | Medium | Project Manager | Ensure customer decision maker with budgetary authority is identified before project start and is part of the project board. Communicate dates for sign-off points up front. | Escalate to project Board and recommend action e.g. to stop the project. |  |  | Who is a senior supplier?
|  | Theft of materials, intellectual property or equipment. | Low | High | High | Project Manager | Follow security procedures, ensure Non-Disclosure Agreements (NDAs), & compliance certificates are in place. Verify all physical security measures in place. Secure insurance. | Notify appropriate authorities e.g. police, project board and initiate internal investigations.
|  | Acts of God for example, extreme weather, leads to loss of resources, materials, premises etc. | Low | High | High | Project Manager | Ensure insurance in place. Familiarise project team with emergency procedures. Where cost effective put back up systems in place e.g. generators. | Notify appropriate authorities. Follow health and safety procedures. Notify stakeholders and Project Board. |  |  | Using insurance for managing risk
|  | Stakeholder action delays project. | Low | High | High | Project Manager | Identify stakeholders, analyse power and influence and create a stakeholder engagement plan. Project Board to authorise the plan. Revisit the plan at regular intervals to check all stakeholders are managed. Consider getting insurance. | Notify appropriate authorities and follow internal procedures e.g. for activist demonstrations. |  |  | Stakeholder Management Templates