## Report
Role | Hours Planned | Actual Hours | Remaining Hours | Original SOW Est. W/ Out Travel
Wireless Engineer | 40 | 8 | 32 | 10100
Project Manager | 10 | 2.25 | 7.75
Total | 50 | 10.25 | 39.75 | Current
2187.5
Expenses | Actual Hours | Value
Travel | 1 | 80
Dining |  | 50
Total | 1 | 130

## Projected
| Planned Hours | Cost Per Hour
Sammy Arden | 40 | 215
Erik Belle | 10 | 150
Travel |  | 80

## Time Entry
Name | Hours | Description
Erik Belle | 1 | Project Setup and Account Intro
Erik Belle | 1 | Staffing and CKOM
Travel | 1 | Sammy to travel from home to site.
Sammy | 8 | Day 1 of wireless survey.
Expense |  | Dining: $50
Erik Belle | 0.25 | Check in with Sammy