## Sheet1
Health | Task Name | Assigned To | State | Start Date | End Date | % Complete | Est. Hours | Actual Hours | Notes
| Project Initiation |  | Complete | May 9th | May 12th | 100% | 3 | 4.5
| Project Setup | Erik | Complete | May 9th | May 9th | 100% | 1 | 1
| Internal Intro | Erik | Complete | May 9th | May 9th | 100% | 1 | 1
| External Intro | Erik | Comnplete | May 10th | May 12th | 100% | 1 | 2 | Issue contacting customer.
| Project Engineer Staffing | Erik | Complete | May 12th | May 13th | 100% | 0.5 | 0.5
| Project Planning |  | Complete | May 16th | May 20th | 100% | 8 | 8
| Kickoff | Erik/Sammy | Complete | May 16th |  | 100% | 4 | 4
| Building Layout Review | Sammy | Complete | May 20th |  | 100% | 4 | 4
| Analyis |  | In progress | May 23rd | May 27th | 16% | 33
| Onsite WSS | Sammy | Blocked | May 23rd |  | 20% | 29 | 8 | Sammy needs access to conference room.
| Results & Recommendations PDF | Sammy |  |  |  |  | 4
| Project Closure |  |  | May 27th | May 30th |  | 4.5
| Results & Recommendations Handoff | Sammy/Erik |  | May 27th |  |  | 2
| Project Closure Meeting | Erik |  | May 30th |  |  | 0.5
| Project Closure Form | Erik |  | May 27th |  |  | 1
| Project Cleanup | Erik |  | May 30th |  |  | 1